## Risk register
TABHOS — Risk Register
Likelihood × Impact rated 1–5. Score = L × I (1–25). Status: Open / Mitigated / Closed.
ID | Category | Risk | L | I | Score | Treatment | Status
R-01 | Confidentiality | Unauthorised access to customer data via stolen credentials | 3 | 5 | 15 | MFA mandatory; quarterly access review; service-role keys not in source | Open
R-02 | Confidentiality | Sensitive data leakage via misconfigured RLS policy | 2 | 5 | 10 | RLS on every table; CI policy test suite; manual review of every policy change | Open
R-03 | Integrity | Malicious or accidental tampering of audit log | 2 | 4 | 8 | Hash-chained audit log with immutable triggers (tamper-evident) | Mitigated
R-04 | Availability | Region-level cloud outage taking platform offline | 3 | 4 | 12 | Sovereign secondary; documented failover | Mitigated
R-05 | Compliance | Personal-data breach without timely notification (PDPA s.28) | 2 | 5 | 10 | 72h notification SLA; IR runbook with timing checklist | Open
R-06 | Operational | Single point of failure on founder (bus factor 1) | 3 | 5 | 15 | Documented runbooks; succession plan; hire plan in investor packet | Open
R-07 | Supply chain | Compromised third-party dependency (npm package supply attack) | 2 | 4 | 8 | SCA + dependency-lock review; minimal dep surface; no unscoped scripts | Open
R-08 | Legal | Tanzania AI Bill imposes requirements not yet met | 2 | 3 | 6 | Akili anticipates sovereignty; engage policy phase actively | Open
R-09 | Reputational | Public security incident before ISO certification | 2 | 4 | 8 | Defence-in-depth; transparent IR; pre-mortem before launch | Open
R-10 | Financial | Cash runway shorter than next funding event | 2 | 5 | 10 | Quarterly cash review; revenue diversification across products | Open
R-11 | Personnel | Loss of key engineer mid-implementation | 3 | 4 | 12 | Documented onboarding; pair-programming; cross-training | Open
R-12 | Technical | Bug-bounty programme not yet launched — researchers find issues anonymously | 3 | 3 | 9 | Launch bug-bounty alongside production milestone | Planned
R-13 | Regulatory | Sub-processor list changes without 30-day notice | 1 | 3 | 3 | Sub-processor governance; legal review of new dependencies | Mitigated
R-14 | Physical | Workstation theft exposing local credentials | 2 | 3 | 6 | Encrypted disks; auto-lock; remote wipe; MFA-only secrets | Mitigated
R-15 | AI-specific | Vendored AI engine produces unsafe output in a clinical context | 2 | 5 | 10 | Provenance + sources required; not a diagnostic tool; clinical-safety review | Open